## Read me
Taps for Rights: Logic Model and Performance Measurement Framework (PMF)
Background document 5 · Water Care AI Hackathon · Track A6
SYNTHETIC TRAINING MATERIAL. Water Care, Taps for Rights, Nimbara and Sundara are fictional. Information has been deliberately altered to include errors, gaps and inconsistencies so you can test whether your tool finds them.
What this workbook is
The approved logic model, activity list and PMF for Taps for Rights, as submitted with the Project Implementation Plan (December 2019). The logic model forms Appendix A-1 of the contribution agreement. The Year 3 report (background document 4) reports actual values against this PMF.
Sheets
Logic Model: ultimate, intermediate and immediate outcomes and outputs, with codes.
Activities: activities under each output, with codes used in the budget template.
PMF: one row per indicator with baseline, end-of-project target, data source, method, frequency and responsibility.
Tips
Codes link everything: 1000 = ultimate outcome; 1100 and 1200 = intermediate outcomes; 1110, 1120, 1210, 1220, 1230 = immediate outcomes; four-digit codes ending in 1-3 = outputs; codes with a decimal = indicators (e.g. 1200.4) or activities (e.g. 1211.2).
Compare this PMF with the agreement (Appendix A) and the Year 3 report. Not everything matches.

## Logic Model
Logic model (Appendix A-1)
Approved with the Project Implementation Plan, December 2019
SYNTHETIC TRAINING MATERIAL. Water Care, Taps for Rights, Nimbara and Sundara are fictional. Information has been deliberately altered to include errors, gaps and inconsistencies so you can test whether your tool finds them.
Level | Code | Result statement | Contributes to
Ultimate outcome | 1000 | Improved comprehensive sexual and reproductive health and rights (SRHR), with a focus on women and adolescent girls, through water, sanitation and menstrual health interventions in Nimbara and Sundara.
Intermediate outcome | 1100 | Increased government and civil society responsiveness to the menstrual health needs of women and adolescent girls. | 1000
Intermediate outcome | 1200 | Increased utilization of gender-sensitive WASH facilities and menstrual hygiene product supplies in schools, health care centres and communities. | 1000
Immediate outcome | 1110 | Enhanced ability of national government officials to take menstrual health needs into account in national level policies and guidelines. | 1100
Immediate outcome | 1120 | Enhanced ability of regional, district and local authorities to take menstrual health needs into account in district level plans and budgets. | 1100
Immediate outcome | 1210 | Enhanced ability of targeted schools and health centres to meet menstrual health needs, including reliable water on site. | 1200
Immediate outcome | 1220 | Enhanced ability of local private sector actors to deliver sustainable supply of menstrual hygiene products. | 1200
Immediate outcome | 1230 | Improved awareness of community members on menstrual health as a foundation of SRHR and gender equality. | 1200
Output | 1111 | Gaps in existing policies and guidelines identified. | 1110
Output | 1112 | Relevant national ministries (water and sanitation, education, health, gender) reached through advocacy and technically supported to address gaps in existing policies and guidelines. | 1110
Output | 1113 | Women influencers at national government level identified, engaged and informed to champion menstrual health as an entry point to SRHR. | 1110
Output | 1121 | Local authorities and service providers trained on menstrual health, including best practice case studies for each country context. | 1120
Output | 1122 | Menstrual health gaps in target districts mapped and used to inform local planning and budgeting processes. | 1120
Output | 1123 | Advocacy carried out for WASH at Work campaigns focused on menstrual health at workplaces and marketplaces. | 1120
Output | 1211 | Water points and WASH facilities in selected schools and health centres rehabilitated and adapted for menstrual hygiene practices. | 1210
Output | 1212 | School and health centre staff trained and engaged on menstrual health and lifecycle implications for SRHR. | 1210
Output | 1213 | Adolescent girl and boy students sensitized on menstrual health through peer-to-peer learning and curriculum as an entry point to SRHR learning. | 1210
Output | 1221 | Existing local supply chains and gaps for menstrual hygiene products comprehensively mapped. | 1220
Output | 1222 | Selected local businesses, women entrepreneurs, women-led and youth-led groups supported to provide and market menstrual hygiene materials. | 1220
Output | 1231 | Local awareness raising campaigns targeting community members on menstrual health implemented through a variety of media. | 1230
Output | 1232 | Community champions for menstrual health identified and trained. | 1230

## Activities
Activities by output
Activity codes are used in the budget template (column 'Activity code')
SYNTHETIC TRAINING MATERIAL. Water Care, Taps for Rights, Nimbara and Sundara are fictional. Information has been deliberately altered to include errors, gaps and inconsistencies so you can test whether your tool finds them.
Activity code | Output | Activity
1111.1 | 1111 | Assess existing national and district policies, plans and guidelines for menstrual health, water and sanitation.
1111.2 | 1111 | Convene meetings across districts to validate the gap analysis.
1112.1 | 1112 | Lead advocacy initiatives with national ministries.
1112.2 | 1112 | Provide technical assistance to ministries to address identified gaps.
1113.1 | 1113 | Lead workshops for women influencers at national level.
1113.2 | 1113 | Engage media to share knowledge on menstrual health.
1121.1 | 1121 | Lead menstrual hygiene management workshops for local authorities and service providers.
1121.2 | 1121 | Develop case studies and training materials for each country context.
1122.1 | 1122 | Analyse district policies, plans and budgets and map menstrual health gaps.
1122.2 | 1122 | Conduct a menstrual health survey in targeted schools and health centres.
1123.1 | 1123 | Assess access gaps for menstrual health in markets and workplaces.
1123.2 | 1123 | Lead district-level WASH at Work advocacy events.
1211.1 | 1211 | Rehabilitate existing school and health centre latrines and water points for menstrual hygiene (water on site, locks, privacy, disposal).
1211.2 | 1211 | Construct new gender-sensitive latrine blocks with a menstrual hygiene room in schools without usable sanitation.
1211.3 | 1211 | Conduct formative research on menstrual hygiene practices and facility use.
1212.1 | 1212 | Train teachers and health centre staff (workshops and refreshers).
1212.2 | 1212 | Lead training workshops for male teachers and health staff.
1213.1 | 1213 | Conduct youth leadership training for peer educators.
1213.2 | 1213 | Engage female and male youth in school WASH clubs and peer-to-peer sessions.
1221.1 | 1221 | Market study of existing supply chains for menstrual hygiene products.
1221.2 | 1221 | Explore opportunities for mobile or community sales points.
1222.1 | 1222 | Train and mentor women- and youth-led groups to make and sell reusable pads.
1231.1 | 1231 | Produce and broadcast radio messages in local languages.
1231.2 | 1231 | Organize Menstrual Hygiene Day and other community events.
1232.1 | 1232 | Identify, train and support community champions.

## PMF
Performance Measurement Framework
Version: Project Implementation Plan, December 2019. Baselines from the baseline survey (October to November 2019).
SYNTHETIC TRAINING MATERIAL. Water Care, Taps for Rights, Nimbara and Sundara are fictional. Information has been deliberately altered to include errors, gaps and inconsistencies so you can test whether your tool finds them.
Code | Result level | Indicator | Disaggregation | Baseline | Target (end of project) | Data source | Collection method | Frequency | Responsibility | Notes
1000.1 | Ultimate outcome | % of women and adolescent girls in targeted communities reporting positive menstrual hygiene management practices | Age group (<15, 15-19, 20+) | Girls <15: 35%; Girls 15-19: 44%; Women 20+: 56% | 75% | Household survey | Survey (sample) | Baseline, midline (Year 3), endline | External evaluator
1100.1 | Intermediate outcome | # of actions by national, provincial or local government officials to address the menstrual health of women and adolescent girls as a result of project assistance | Country; level of government | 0 | 18 | Advocacy tracker | Document review | Annual | Country programme M&E officers
1100.2 | Intermediate outcome | # of national policies, guidelines and strategies relating to, or including, menstrual health strengthened or enacted as a result of project assistance | Country | 0 | 3 | Policy documents | Document review | Annual | Country programme advocacy leads
1100.3 | Intermediate outcome | # of actions by civil society organizations to address the menstrual health of women and adolescent girls as a result of project assistance | Country; type of organization | 0 | 6 | Advocacy tracker | Document review | Annual | Local partners
1200.1 | Intermediate outcome | % of adolescent girls in targeted schools reporting sanitation and hygiene facilities are acceptable for them | Age group | 1% | 80% | School survey | Survey (sample) | Baseline, midline, endline | External evaluator
1200.2 | Intermediate outcome | % of women and adolescent girls in targeted health care facilities reporting sanitation and hygiene facilities are acceptable for them | Age group | 0.3% | 70% | Exit interviews | Structured interviews | Baseline, midline, endline | External evaluator
1200.3 | Intermediate outcome | % of women and adolescent girls in targeted communities using acceptable hygienic products for menstruation when needed | Age group (<15, 15-19, 20+) | Girls <15: 21%; Girls 15-19: 28%; Women 20+: 36% | 50% | Household survey | Survey (sample) | Baseline, midline, endline | External evaluator
1200.4 | Intermediate outcome | % of targeted schools and health care facilities with water available on premises at the time of visit | Facility type; country | 38% | 85% | Facility checklist | Spot check (unannounced) | Semi-annual | Country programme M&E officers | Added at baseline
1110.1 | Immediate outcome | % of targeted national government and civil society stakeholders with positive knowledge of menstrual health (on a scale) | Sex | Women: 70%; Men: 68% | 35% | KAP survey | Questionnaire | Baseline, midline, endline | External evaluator
1120.1 | Immediate outcome | % of local government and civil society stakeholders with positive knowledge of menstrual hygiene management (on a scale) | Sex | Women: 40%; Men: 24% | 70% | KAP survey | Questionnaire | Baseline, midline, endline | External evaluator
1120.2 | Immediate outcome | % of total budget allocation within local government budgets in target areas for menstrual health in schools and health care facilities | District | 0% | 15% | District budgets | Document review | Annual | Country programme advocacy leads
1120.3 | Immediate outcome | # and % of targeted schools and health care facilities with gender-sensitive sanitation for menstrual health included in plans | Institution type | Schools: 1 (3%); HCFs: 1 (5%) | 50% | School and facility plans | Document review | Annual | Local partners
1210.1 | Immediate outcome | % of health centre staff and teachers with positive knowledge of menstrual hygiene management (on a scale) | Sex; role | HCF staff: M 55%, W 41%; Teachers: M 42%, W 28% | 80% | KAP survey | Questionnaire | Baseline, midline, endline | External evaluator
1210.2 | Immediate outcome | # and % of targeted schools with provision for menstrual hygiene management (water, private space, disposal) | Country | 6 (15%) | 60% | Facility checklist | Observation | Semi-annual | Country programme M&E officers
1210.3 | Immediate outcome | # and % of targeted health care facilities with basic hygienic and sanitation facilities and menstrual hygiene products | Country | 1 (5%) | 50% | Facility checklist | Observation | Semi-annual | Country programme M&E officers
1220.1 | Immediate outcome | # of local private sector actors producing menstrual hygiene products | Sex | 0 | To be set after market mapping | Partner records | Register | Annual | Local partners | Market mapping planned for Year 1
1230.1 | Immediate outcome | % of community members in targeted areas with positive knowledge of menstrual hygiene management (on a scale) | Sex; age group | Girls 10-14: 14%; 15-19: 13%; Women 20+: 24%; Boys 10-14: 8%; 15-19: 14%; Men 20+: 15% | 70% | Household survey | Survey (sample) | Baseline, midline, endline | External evaluator
1230.2 | Immediate outcome | # of local actors promoting menstrual hygiene management in target communities as a result of project assistance | Sex; age group; public or private | 0 | 150 | Partner records | Register | Semi-annual | Local partners